# Harbourline Home & Garden - Elmbridge FC Tender Specification

Version 2.0, issued 2 October 2026 by Harbourline Procurement. Requirements marked M are mandatory, D desirable.

# 1. Throughput and capacity

TP-01 - Peak hour throughput of 6,000 order lines in Black Friday week (M)

TP-02 - AS/RS capacity for 60,000 totes, with 20% free locations at peak (M)

TP-03 - Goods-to-person ports at 450 picks per hour per port (M)

TP-04 - Same-day despatch for orders placed before 20:00 (M)

TP-05 - Bulky items (over 30 kg or 1.2 m) handled outside the automation (M)

# 2. Software and integration

Replacement of the 2009 in-house WMS by the supplier's WMS, integrated with Microsoft Dynamics 365 Finance and Operations for item master, purchase orders, sales orders and stock adjustments.

Real-time stock visibility in Dynamics 365 within 2 minutes of a movement.

Two parcel carriers (to be chosen in Q1 2027): labels, manifests and tracking events.

Staff single sign-on.

Dashboards for throughput, port utilisation and order backlog, visible on the warehouse floor.

# 3. Non-functional

Availability 99.7% during operating hours (06:00-24:00, 7 days).

Recovery from a WMS server failure within 30 minutes.

Audit trail of stock adjustments kept for 7 years.

# 4. Programme

Contract award mid-December 2026; site access from 15 January 2027.

Go-live by 1 August 2027, so peak trials can run in September.

Training for 160 operators and 12 super-users, including a night shift.

# 5. Commercial

Fixed price including named allowances for unknowns, each with its hours.

Liquidated damages of GBP 10,000 per day of delay to go-live.

Spare parts held on site for the first two years.